## PLan
Activity | Responsibility | Timeframe | Method | Resources | Additional Information
Objective 1: Sharing knowledge
Set up and maintain mitigation page on the CCWG website | NGORC | March | Group members to provide content (documents, events) and links to NGORC. Initial information to be submitted to Rowena (FRR) by 18th April. After this send any new resources directly to NGORC. | NGORC (website) with input from group members | Website created in March, content required
Call for CCWG poster/material contributions at APFW session | SNV - all mitigation group members | April 21-26 | Group members to provide materials to SNV prior to April 21st | SNV to arrange space at APFW session, group members to contribute materials | APFW website: http://www.fao.org/forestry/site/44755/en/0/
Contribute to CCWG quarterly newsletter | NGORC - all group members | ongoing | Rotating quarterly responsibility for collecting submissions from mitigation group members, according to template provided by NGORC. Newsletter circulated to CCWG mailing list
Set up and participate in online learning group for climate change mitigation | CARE | March onwards | CARE to invite group members to online learning group | none required | invitations sent in March
Objective 2: Knowledge and capacity building
Organise open CCWG meeting on REDD as side event to APFW | SNV | April 24th | Identify and contact REDD expert. Propose meeting through CCWG core group, Send invitiation through CCWG mailing list | NGORC (venue and communication), SNV (transport and logistics for expert within Hanoi), Individual participants (own transport and attendance costs) | IUCN expert contacted and committed.
Presentations at mitigation group meetings | All | Ongoing from April | Topic and presenter to be decided at each thematic group meeting and location, resources arranged accordingly. Potential for invitations to CCWG members outside thematic group. Mai on Clean Fund? Plan Vivo? | Variable
Climate change mitigation mapping of activities and expertise | SNV - as thematic group coordinator | Ongoing from April | Compile profiles of thematic group members and mitigation activities (using C2C template?). Build up database as we learn about new organisations/activities in Vietnam | Time?
Share sources of funding for climate change mitigation programming and related NGO capacity building | All (INGOs in particular) | ongoing | Passing information on funding opportunities to other thematic group members and the wider CCWG through mailing list, newsletter. Inviting donor reps and fund managers to speak to group meetings
Capacity building needs assessment workshop for Vietnamese NGOs | ? | May-July | Combine with adaptation thematic group in a joint needs assessment workshop proposal to CCWG core group. Discuss at next core group meeting 28th April | ???
Objective 3: Developing institutional frameworks
Objective 4: Engaging with private sector

## Acronyms
Acronyms
VGBC | Vietnam Green Building Council
EMW | East Meets West
C2C | Challenge to Change
CARE | Care International
NGO RC | VUFO-NGO Resource Centre
NDMP | National Disaster Mitigation Partnership
DMWG | Disaster Management Working Group
CCWG | Climate Change Working Group